## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Obtaining Tablets
Work with Downtown branch general manager to determine the needed tablets quantity. |  |  |  | 0
Work with North branch general manager to determine the needed tablets quantity. |  |  |  | 0
Taking descision about backup tablets. |  |  |  | 0
Comparing the vendor tablets offerings that meet requirements. |  |  |  | 0
Create contracts and statements of work for vendors. |  |  |  | 2
Buy and receive the correct number of tablets. |  |  |  | 10
Milestone: Tablets Installation
Connect the marketing team with Terrific Tablets for brand development and digital menu creation. |  |  |  | 0
Collaborate with the tablet provider to discover frequent difficulties and turnaround times for fixing tablet issues. |  |  |  | 10 | Carter
Create corporate policies and troubleshooting manuals for tablet deployment and use. |  |  |  | 1 | Deanna, Carter, Marketing
Examine the work needed to ensure that tablets connect seamlessly with the existing POS and host system. |  |  |  | 2 | Peta
Determine a place for backup tablets. |  |  |  | 3 | Peta
Identify bar section tables that require correct wiring by an electrician. |  |  |  | 3
Install one tablet to guarantee correct installation and the identification of any potential problems.
Obtain the services of an electrician to connect appropriate tables at the Downtown site.
Obtain the services of an electrician to connect appropriate tables at the North site. |  |  |  | 7 | Peta/Seydou
Tablets can now have highlighted menu items and coupon values. |  |  |  | 1 | Seydou
Consult with Carter about prospective menu changes. |  |  |  | 2 | Seydou
7
Milestone: Train Employees
Create a training program and a deployment plan.
A pre-training meeting will be held to present tablets and adjustments. |  |  |  | 0
Seydou will teach GMs and key personnel on tablet technology. |  |  |  | 0
Coordination, scheduling, and holding meetings to discuss rollout and report questions/concerns with GMs. |  |  |  | 3
3
Milestone: Alpha Testing
Hold an alpha testing with staff family and friends to simulate full service.
Gather comments from the test and identify areas for improvement. |  |  |  | 0
Implement test feedback |  |  |  | 1
3
Milestone: Launch Day
Determine launch day date and time.
Prepare for launch day by collaborating with GMs and identifying outstanding needs. |  |  |  | 0
Launch day |  |  |  | 2
0
Milestone: Install Upgraded Devices Post-Launch
Replace the plugs on new tablets.
2

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Obtaining Tablets
Work with Downtown branch general manager to determine the needed tablets quantity. |  | 0 | 0 | 0 | 1 | H
Work with North branch general manager to determine the needed tablets quantity. |  | 0 | 0 | 0 | 1 | H
Taking descision about backup tablets. |  | 0 | 0 | 0 | 1 | H
Comparing the vendor tablets offerings that meet requirements. |  | 1 | 1 | 1 | 2 | H
Create contracts and statements of work for vendors. |  | 2 | 1 | 2 | 3 | H
Buy and receive the correct number of tablets. |  | 10 | 7 | 10 | 14 | H
Milestone: Tablets Installation
Connect the marketing team with Terrific Tablets for brand development and digital menu creation. |  | 0 | 0 | 0 | 1 | H
Collaborate with the tablet provider to discover frequent difficulties and turnaround times for fixing tablet issues. |  | 2 | 1 | 2 | 4 | H
Create corporate policies and troubleshooting manuals for tablet deployment and use. |  | 3 | 1 | 2 | 4 | M
Examine the work needed to ensure that tablets connect seamlessly with the existing POS and host system. |  | 3 | 1 | 3 | 4 | L
Determine a place for backup tablets. |  | 0 | 0 | 0 | 1 | H
Identify bar section tables that require correct wiring by an electrician. |  | 0 | 0 | 0 | 1 | H
Install one tablet to guarantee correct installation and the identification of any potential problems. |  | 0 | 0 | 0 | 1 | M
Obtain the services of an electrician to connect appropriate tables at the Downtown site. |  | 3 | 2 | 3 | 4 | M
Obtain the services of an electrician to connect appropriate tables at the North site. |  | 3 | 2 | 3 | 4 | M
Tablets can now have highlighted menu items and coupon values. |  | 1 | 0 | 1 | 2 | M
Consult with Carter about prospective menu changes. |  | 10 | 4 | 10 | 14 | M
Milestone: Train Employees
Create a training program and a deployment plan. |  | 7 | 7 | 7 | 10 | H
A pre-training meeting will be held to present tablets and adjustments. |  | 1 | 1 | 1 | 2 | H
Seydou will teach GMs and key personnel on tablet technology. |  | 2 | 2 | 2 | 3 | H
Coordination, scheduling, and holding meetings to discuss rollout and report questions/concerns with GMs. |  | 7 | 7 | 10 | 14 | L
Milestone: Alpha Testing
Hold an alpha testing with staff family and friends to simulate full service. |  | 0 | 0 | 0 | 1 | H
Gather comments from the test and identify areas for improvement. |  | 1 | 0 | 1 | 2 | M
Implement test feedback |  | 3 | 1 | 2 | 4 | L
Milestone: Launch Day
Determine launch day date and time. |  | 0 | 0 | 0 | 1 | H
Prepare for launch day by collaborating with GMs and identifying outstanding needs. |  | 2 | 1 | 2 | 4 | H
Launch day |  | 0 | 0 | 0 | 0 | H
Milestone: Install Upgraded Devices Post-Launch
Replace the plugs on new tablets.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction - faster, more efficient experience | Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | FALSE
Customer Satisfaction - faster, more efficient experience | Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | FALSE
Customer Satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | FALSE
Customer Satisfaction - faster, more efficient experience | 100% order accuracy |  |  | FALSE
Customer Satisfaction - faster, more efficient experience | Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your appetizers? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your entrees? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How long did it take you to complete the checkout process today? | Multiple choice | less than a minute | 1-3 minutes | more than 3 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How satisfied are you using the tablet to checkout? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | Did you encounter any issues using the tablet? | Yes/No | Yes. Please explain: | No
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | How was your experience using the tablet to order your meal today? | Open-ended | Please explain:
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you satisfied with your meal today? | Yes/No | Yes | No
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you able to order exactly what you wanted? If no, please explain. | Yes/No | Yes | No. Please explain:
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | How long did you have to wait before being seated today? | Multiple choice | 0-5 min | 5-10 min | 10-15min | 15 or more min
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | Were you satisfied with your wait time today? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied